{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","進捗入力","進捗"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":3,"n_cols":2,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
[null,"休日"]
[null,"2018-04-30"]
[null,"2018-05-03"]

{"sheet":"進捗入力","index":1,"n_rows":6,"n_cols":11,"rows_kept":6,"cut":false,"hidden":false,"merged":[]}
[]
[]
[null,"№","作業項目","日数","休日","開始日付","終了日付","担当","予定\n進捗","実際\n進捗","状況"]
[null,1,{"$f":"進捗!C6","v":"作業A"},{"$f":"進捗!D6","v":3},{"$f":"進捗!E6","v":0},{"$f":"進捗!F6","v":"2018-04-09"},{"$f":"進捗!G6","v":"2018-04-11"},{"$f":"進捗!H6","v":"佐藤"},{"$f":"進捗!J6","v":0.67},0.65]
[null,2,{"$f":"進捗!C7","v":"作業B"},{"$f":"進捗!D7","v":6},{"$f":"進捗!E7","v":2},{"$f":"進捗!F7","v":"2018-04-09"},{"$f":"進捗!G7","v":"2018-04-16"},{"$f":"進捗!H7","v":"山田"},{"$f":"進捗!J7","v":0.68},0.68]
[null,3,{"$f":"進捗!C8","v":"作業C"},{"$f":"進捗!D8","v":7},{"$f":"進捗!E8","v":1},{"$f":"進捗!F8","v":"2018-04-11"},{"$f":"進捗!G8","v":"2018-04-18"},{"$f":"進捗!H8","v":"佐藤"},0.5,0.49]

{"sheet":"進捗","index":2,"n_rows":8,"n_cols":43,"rows_kept":8,"cut":false,"hidden":false,"merged":[[2,3,2,4]]}
[]
[]
[null,null,"作業期間","2018-04-01",null,"～","2018-05-01"]
[null,null,null,null,null,null,null,null,null,null,null,null," 4月",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null," 5月"]
[null,"№","作業項目","日数","休日","開始日付","終了日付","担当","色","予定\n進捗","実際\n進捗","状況",1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,1]
[null,1,"作業A",3,0,"2018-04-09",{"$f":"F6+D6+E6-1","v":"2018-04-11"},"佐藤",null,0.67,{"$f":"進捗入力!J4","v":0.65}]
[null,2,"作業B",6,2,"2018-04-09",{"$f":"F7+D7+E7-1","v":"2018-04-16"},"山田",null,0.68,{"$f":"進捗入力!J5","v":0.68}]
[null,3,"作業C",7,1,"2018-04-11",{"$f":"F8+D8+E8-1","v":"2018-04-18"},"佐藤",null,0.5,0.5]